Name: ______________________________	Date: ________

# Chapter 37: Base knowledge worksheet

Full sentence answers are not required: HL 24 marks, 40 minutes

1	a	Draw a network diagram for project X with EST and LFT clearly shown on each

node and the critical path clearly labelled.					(10)

Order of tasks for project X

| Activity | Preceding activities | Duration (in days) |
| --- | --- | --- |
| A | – | 2 |
| B | A | 3 |
| C | A, B | 4 |
| D | A, B, C, E, F | 5 |
| E | – | 8 |
| F | E | 9 |
| G | E, F | 10 |
| H | D, G | 6 |

b	Calculate the total float and free float for all non-critical activities. (Hint: show all

working and formulae used.) 								(10)

| Activity | EST | LFT | Duration (days) | Total float (days) | Free float (days) |
| --- | --- | --- | --- | --- | --- |
| A |  |  |  |  |  |
| B |  |  |  |  |  |
| C |  |  |  |  |  |
| D |  |  |  |  |  |

2	What does total float tell managers?							(2)

3	What does free float tell managers?							(2)