# Chapter 37: Worksheet mark scheme (24 marks)

1	a	Draw a network diagram for project X with EST and LFT clearly shown on each

node and the critical path clearly labelled.					(10)

Order of tasks for project X

| Activity | Preceding activities | Duration (in days) |
| --- | --- | --- |
| A | – | 2 |
| B | A | 3 |
| C | A, B | 4 |
| D | A, B, C, E, F | 5 |
| E | – | 8 |
| F | E | 9 |
| G | E, F | 10 |
| H | D, G | 6 |

Critical path analysis diagram for project X

10 marks:

A correct CPA with the critical path, ESTs and LFTs clearly marked and a key included. The direction of the dependency of the dummy activity is correctly marked in the direction F → C.

8–9 marks:

Up to two minor errors, but the dummy activity is recognised. No more than 8 marks should be awarded if the dummy activity is represented by activities converging on a single node.

6–7 marks:

Up to three errors. Award a maximum of 6 marks if no key is included.

4–5 marks:

A CPA with no key and/or four or more errors.

2–3 marks:

The candidate has the basic idea of drawing a CPA but displays little understanding of the principles involved in calculating EST or LFT.

1 mark:

CPA attempted.

b	Calculate the total float and free float for all non-critical activities. (Hint: show all

working and formulae used.) 								(10)

| Activity | EST | LFT | Duration (days) | Total float (days) LFT – duration – EST | Free float (days) EST (next activity) – duration – EST (this activity) |
| --- | --- | --- | --- | --- | --- |
| A | 0 | 15 | 2 | 13 | 0 |
| B | 2 | 18 | 3 | 13 | 0 |
| C | 5 | 22 | 4 | 13 | 8 |
| D | 17 (EST next 27) | 27 | 5 | 5 | 5 |

Award 1 mark for correct total float formula, 1 mark for correct free float formula and 1 mark each for correct calculation of floats (up to a maximum of 8 marks – no marks possible if formulae used are incorrect).

2	What does total float tell managers?							(2)

This is the amount of time an activity can be delayed without delaying the whole project.

3	What does free float tell managers?							(2)

This is the amount of time an activity can be delayed without delaying the start of the following activities.